This checklist is designed to confirm if a project is following the Software Project Management processes specified for NASA software. It contains the Software Engineering (SWE) Requirements and associated Software Assurance & Software Safety Tasks that are applicable to the Software Project Management and used to formally audit its processes. This checklist also audits the Software Assurance processes. This checklist is specific to software but may be modified to address the needs of the project or organization. The audit schedule for the Software Project Planning and Management process is available in Topic 8.59 - Audit Reports.

# Document Information

This audit was performed on: [Document/records name, identifier/number, revision, date]

Link to document: [Link to document/records]

Notes:

The NASA Software Engineering and Assurance Handbook (NASA-HDBK-2203) for NPR 7150.2D and NASA-STD-8739.8B should be referenced when performing this audit as it may provide context and insight for the topic at hand.

| # NPR 7150.2D Audit Findings Details Do the Software Project Management processes address the following: |  |  |  |  |
| --- | --- | --- | --- | --- |
| SWE Requirement Text | SWE # | Software Assurance and Software Safety Tasks | Compliant (FC/PC/ NC/NA)? | Evidence and Comments |
| ## Software Project Planning and Management – These requirements should be checked during both the Planning Audit and the Management Process Audits. |  |  |  |  |
| The project manager shall develop, maintain, and execute software plans, including security plans, that cover the entire software life cycle and, as a minimum, address the requirements of this directive with approved tailoring. | SWE-013 | - 2. Develop and maintain a Software Assurance Plan following the content defined in NASA-HDBK-2203 for a software assurance plan, including software safety. |  |  |
| The project manager shall establish and maintain the software processes, software documentation plans, list of developed electronic products, deliverables, and list of tasks for the software development that are required for the project’s software developers, as well as the action required (e.g., approval, review) of the Government upon receipt of each of the deliverables. | SWE-036 | - Confirm the following are approved, implemented, and updated per requirements: - Software processes, including software assurance, software safety, and IV&V processes, Software documentation plans, List of developed electronic products, deliverables, and List of tasks required or needed for the project’s software development. |  |  |
|  |  | - Confirm that any required government actions are established and performed upon receipt of deliverables (e.g., approvals, reviews). |  |  |
| The project manager shall plan, track, and ensure project specific software training for project personnel. | SWE-017 | - Confirm that any project-specific software training has been planned, tracked, and completed for project personnel, including software assurance and software safety personnel. |  |  |
| The project manager, in conjunction with the SMA organization, shall determine if each software component is considered to be safety-critical per the criteria defined in NASA-STD-8739.8. | SWE-205 | - 5. Develop and maintain a software safety analysis throughout the software development life cycle. |  |  |
| The project manager shall identify cybersecurity risks, along with their mitigations, in flight and ground software systems, and plan the mitigations for these systems. | SWE-154 | - Confirm that cybersecurity risks, along with their mitigations, are identified and managed. |  |  |
| The project manager shall plan and conduct software regression testing to demonstrate that defects have not been introduced into previously integrated or tested software and have not produced a security vulnerability. | SWE-191 | - Confirm that the project plans regression testing and that the regression testing is adequate and includes retesting of all safety-critical code components. |  |  |
| The project manager shall establish, record, maintain, report, and utilize software management and technical measurements. | SWE-090 | - Confirm that a measurement program establishes, records, maintains, reports, and uses software assurance, management, and technical measures. |  |  |
| ## Software Project Management |  |  |  |  |
| The project manager shall define and document the milestones at which the software developer(s) progress will be reviewed and audited. | SWE-037 | - 2. Participate in project milestones reviews. |  |  |
| The project manager shall require the software developer(s) to periodically report status and provide insight into software development and test activities; at a minimum, the software developer(s) will be required to allow the project manager and software assurance personnel to: a. Monitor product integration. b. Review the verification activities to ensure adequacy. c. Review trade studies and source data. d. Audit the software development processes and practices. e. Participate in software reviews and technical interchange meetings. | SWE-039 | - Confirm that software developer(s) periodically report status and provide insight to the project manager. |  |  |
|  |  | - Monitor product integration. |  |  |
|  |  | - Analyze the verification activities to ensure adequacy. |  |  |
|  |  | - Assess trade studies, source data, software reviews, and technical interchange meetings. |  |  |
|  |  | - Perform audits on software development processes and practices at least once every two years. |  |  |
|  |  | - Develop and provide status reports. |  |  |
|  |  | - Develop and maintain a list of all software assurance review discrepancies, risks, issues, findings, and concerns. |  |  |
|  |  | - Confirm that the project manager provides responses to software assurance and software safety submitted issues, findings, and risks and that the project manager tracks software assurance and software safety issues, findings, and risks to closure. |  |  |
| The project manager shall require the software developer(s) to provide NASA with software products, traceability, software change tracking information, and nonconformances in electronic format, including software development and management metrics. | SWE-040 | - Confirm that software artifacts are available in electronic format to NASA. |  |  |
| The project manager shall comply with the requirements in this NPR that are marked with an “X” in Appendix C consistent with their software classification. | SWE-139 | - Assess that the project's software requirements, products, procedures, and processes are compliant with the NPR 7150.2 requirements per the software classification and safety criticality for software. |  |  |
| Each project manager with software components shall maintain a requirements mapping matrix or multiple requirements mapping matrices against requirements in this NPR, including those delegated to other parties or accomplished by contract vehicles or Space Act Agreements. | SWE-125 | - Confirm that the project maintains a requirements mapping matrix (matrices) for all requirements in NPR 7150.2. |  |  |
|  |  | - Maintain the requirements mapping matrix (matrices) for requirements in NASA-STD-8739.8. |  |  |
| The project manager shall satisfy the following conditions when a COTS, GOTS, MOTS, OSS, or reused software component is acquired or used: - The requirements to be met by the software component are identified. - The software component includes documentation to fulfill its intended purpose (e.g., usage instructions). - Proprietary rights, usage rights, ownership, warranty, licensing rights, transfer rights, and conditions of use (e.g., required copyright, author, and applicable license notices within the software code, or a requirement to redistribute the licensed software only under the same license (e.g., GNU GPL, ver. 3, license)) have been addressed and coordinated with Center Intellectual Property Counsel. - Future support for the software product is planned and adequate for project needs. - The software component is verified and validated to the same level required to accept a similar developed software component for its intended use. - The project has a plan to perform periodic assessments of vendor reported defects to ensure the defects do not impact the selected software components. | SWE-027c | - Confirm that the conditions listed in "a" through "f" are complete for any COTS, GOTS, MOTS, OSS, or reused software that is acquired or used. - c. Proprietary rights, usage rights, ownership, warranty, licensing rights, transfer rights, and conditions of use (e.g., required copyright, author, and applicable license notices within the software code, or a requirement to redistribute the licensed software only under the same license (e.g., GNU GPL, ver. 3, license)) have been addressed and coordinated with Center Intellectual Property Counsel. |  |  |
| The project manager shall regularly hold reviews of software schedule activities, status, performance metrics, and assessment/analysis results with the project stakeholders and track issues to resolution. | SWE-018 | - Confirm the generation and distribution of periodic reports on software schedule activities, metrics, and status, including reports of software assurance and software safety schedule activities, metrics, and status. |  |  |
|  |  | - Confirm closure of any project software schedule issues. |  |  |
| The project manager shall require the software developer(s) to provide a software schedule for the project’s review, and schedule updates as requested. | SWE-046 | - Confirm the project's schedules, including the software assurance’s/software safety’s schedules, are updated. |  |  |
| The project manager shall plan, track, and ensure project specific software training for project personnel. | SWE-017 | - 2. Confirm that software assurance and software safety personnel have completed the appropriate software assurance and/or software safety training to satisfactorily conduct assurance and safety activities. |  |  |
| The project manager shall maintain records of each software classification determination, each software Requirements Mapping Matrix, and the results of each software independent classification assessments for the life of the project. | SWE-176 | - Confirm that records of the software Requirements Mapping Matrix and each software classification are maintained and updated for the life of the project. |  |  |
| The project manager shall plan and implement software assurance, software safety, and IV&V (if required) per NASA-STD-8739.8, Software Assurance and Software Safety Standard. | SWE-022 | - Perform software assurance, software safety, and IV&V (if required) according to the software assurance and software safety standard requirements in NASA-STD-8739.8, Software Assurance and Software Safety Standard, and the Project’s software assurance plan. |  |  |
| For projects reaching Key Decision Point A, the program manager shall ensure that software IV&V is performed on the following categories of projects: - Category 1 projects as defined in NPR 7120.5. Category 2 projects as defined in NPR 7120.5, that have Class A or Class B payload risk classification per NPR 8705.4, Risk Classification for NASA Payloads. Projects selected explicitly by the Mission Directorate Associate Administrator to have software IV&V. | SWE-141 | - Confirm that IV&V requirements (section 4.4) are complete on projects required to have IV&V. |  |  |
| If software IV&V is performed on a project, the project manager shall ensure that IV&V is provided access to development artifacts, products, source code, and data required to perform the IV&V analysis efficiently and effectively. | SWE-178 | - Confirm that IV&V has access to the software development artifacts, products, source code, and data required to perform the IV&V analysis efficiently and effectively. |  |  |
| If software IV&V is performed on a project, the project manager shall provide responses to IV&V submitted issues and risks and track these issues and risks to closure. | SWE-179 | - Confirm that the project manager responds to IV&V submitted issues, findings, and risks and that the project manager tracks IV&V issues, findings, and risks to closure. |  |  |
| The project manager shall define the approach to the automatic generation of software source code, including: - Validation and verification of auto-generation tools. - Configuration management of the auto-generation tools and associated data. - Description of the limits and the allowable scope for the use of the auto-generated software. - Verification and validation of auto-generated source code using the same software standards and processes as hand-generated code. - Monitoring the actual use of auto-generated source code compared to the planned use. - Policies and procedures for making manual changes to auto-generated source code. - Configuration management of the input to the auto-generation tool, the output of the auto-generation tool, and modifications made to the output of the auto-generation tools. | SWE-146 | - Assess that the approach for the auto-generation software source code is defined, and the approach satisfies at least the conditions “a” through “g.” - Validation and verification of auto-generation tools. Configuration management of the auto-generation tools and associated data. Description of the limits and the allowable scope for the use of the auto-generated software. Verification and validation of auto-generated source code using the same software standards and processes as hand-generated code. Monitoring the actual use of auto-generated source code compared to the planned use. Policies and procedures for making manual changes to auto-generated source code. Configuration management of the input to the auto-generation tool, the output of the auto-generation tool, and modifications made to the output of the auto-generation tools. |  |  |
| The project manager shall require the software developers and custom software suppliers to provide NASA with electronic access to the models, simulations, and associated data used as inputs for auto-generation of software. | SWE-206 | - Confirm that NASA, engineering, project, software assurance, and IV&V have electronic access to the models, simulations, and associated data used as inputs for auto-generation of software. |  |  |
| The project manager shall acquire, develop, and maintain software from an organization with a non-expired CMMI®-DEV rating as measured by a CMMI® Institute Certified Lead Appraiser as follows: - For Class A software: CMMI®-DEV Maturity Level 3 Rating or higher for software. For Class B software (except Class B software on NASA Class D payloads, as defined in NPR 8705.4): CMMI®-DEV Maturity Level 2 Rating or higher for software. | SWE-032 | - 3. Perform audits on the software development and software assurance processes. |  |  |
| The project manager shall evaluate software for potential reuse by other projects across NASA and contribute reuse candidates to the appropriate NASA internal sharing and reuse software system. However, if the project manager is not a civil servant, then a civil servant will pre-approve all such software contributions; all software contributions should include, at a minimum, the following information: - Software Title. - Software Description. - The Civil Servant Software Technical POC for the software product. - The language or languages used to develop the software. - Any third-party code contained therein, and the record of the requisite license or permission received from the third party permitting the Government’s use and any required markings (e.g., required copyright, author, applicable license notices within the software code, and the source of each third-party software component (e.g., software URL & license URL)), if applicable. - Release notes. | SWE-148 | - Confirm that any project software contributed as a reuse candidate has the identified information in items “a” through “f.” - Software Title. Software Description. The Civil Servant Software Technical POC for the software product. The language or languages used to develop the software. Any third-party code contained therein, and the record of the requisite license or permission received from the third party permitting the Government’s use and any required markings (e.g., required copyright, author, applicable license notices within the software code, and the source of each third-party software component (e.g., software URL & license URL)), if applicable. Release notes. |  |  |
| The project manager shall perform a software cybersecurity assessment on the software components per the Agency security policies and the project requirements, including risks posed by the use of COTS, GOTS, MOTS, OSS, or reused software components. | SWE-156 | - Confirm the project has performed a software cybersecurity assessment on the software components per the Agency security policies and the project requirements, including risks posed by the use of COTS, GOTS, MOTS, OSS, or reused software components. |  |  |
| The project manager shall identify, initiate corrective actions, and track until closure inconsistencies among requirements, project plans, and software products. | SWE-054 | - Monitor identified differences among requirements, project plans, and software products and confirm differences are addressed and corrective actions are tracked until closure. |  |  |
| The project manager shall ensure that the code coverage measurements for the software are selected, implemented, tracked, recorded, and reported. | SWE-189 | - Confirm that code coverage measurements have been selected, performed, tracked, recorded, and communicated with each release. |  |  |
| The project manager shall plan and implement software operations, maintenance, and retirement activities. | SWE-075 | - 2. Confirm that the project implements software operations, software maintenance, and software retirement plans. |  |  |
| The project manager shall complete, prior to delivery, verification that all software requirements identified for this delivery have been met or dispositioned, that all approved changes have been implemented, and that all defects designated for resolution prior to delivery have been resolved. | SWE-194 | - 2. Confirm that the project has met all software requirements identified for delivery. |  |  |
|  |  | - 3. Confirm requirements once planned for delivery but no longer appearing in delivery documentation have been dispositioned. |  |  |
|  |  | - 4. Confirm that approved changes have been implemented and tested. |  |  |
|  |  | - 6. Approve or sign off on the projects delivered products. |  |  |
| The project manager shall maintain the software using standards and processes per the applicable software classification throughout the maintenance phase. | SWE-195 | - Perform audits on the standards and processes used throughout maintenance based on the software classification. |  |  |
| The project manager shall track and evaluate changes to software products. | SWE-080 | - 2. Confirm the following: - The project tracks the changes. - The changes are approved and documented before implementation. - The implementation of changes is complete. - The project tests the changes. |  |  |
| The project manager shall participate in any joint NASA/developer audits. | SWE-045 | - Participate in or assess the results from any joint NASA/developer audits. Track any findings to closure. |  |  |
| The project manager shall record, analyze, plan, track, control, and communicate all of the software risks and mitigation plans. | SWE-086 | - 2. Perform audits on the risk management process for the software activities. |  |  |
| The project manager shall establish, record, maintain, report, and utilize software management and technical measurements. | SWE-090 | - 2. Perform trending analyses on metrics (quality metrics, defect metrics) and report. |  |  |
|  |  | - 3. Collect any identified organizational metrics and submit them to the organizational repository. |  |  |
| The project manager shall analyze software measurement data collected using documented project-specified and Center/organizational analysis procedures. | SWE-093 | - Confirm software measurement data analysis conforms to documented analysis procedures. |  |  |
|  |  | - Analyze software assurance measurement data. |  |  |
| The project manager shall provide access to the software measurement data, measurement analyses, and software development status as requested to the sponsoring Mission Directorate, the NASA Chief Engineer, the Center Technical Authorities, HQ SMA, and other organizations as appropriate. | SWE-094 | - Confirm access to software measurement data, analysis, and status as requested to the following entities, at a minimum: - - Sponsoring Mission Directorate - - NASA Chief Engineer - - Center Technical Authorities - - Headquarters SMA |  |  |
| The project manager shall monitor measures to ensure the software will meet or exceed performance and functionality requirements, including satisfying constraints. | SWE-199 | - Confirm that the project monitors and updates planned measurements to ensure the software meets or exceeds performance and functionality requirements, including satisfying constraints. |  |  |
|  |  | - Monitor and track any performance or functionality requirements that are not being met or are at risk of not being met. |  |  |
| The project manager shall collect, track, and report software requirements volatility metrics. | SWE-200 | - Confirm that the project collects, tracks, and reports on the software volatility metrics. |  |  |
|  |  | - Analyze software volatility metrics to evaluate requirements stability as an early indicator of project problems. |  |  |
| The project manager shall track and maintain software non-conformances (including defects in tools and appropriate ground software). | SWE-201 | - Confirm that all software non-conformances are recorded and tracked to resolution. |  |  |
| The project manager shall define and implement clear software severity levels for all software non-conformances (including tools, COTS, GOTS, MOTS, OSS, reused software components, and applicable ground systems). | SWE-202 | - 3. Confirm that the project assigns severity levels to non-conformances associated with tools, COTS, GOTS, MOTS, OSS, and reused software components. |  |  |
|  |  | - 4. Maintain or access the number of software non-conformances at each severity level for each software configuration item. |  |  |
| The project manager shall implement mandatory assessments of reported non-conformances for all COTS, GOTS, MOTS, OSS, and/or reused software components. | SWE-203 | - Confirm the evaluations of reported non-conformances for all COTS, GOTS, MOTS, OSS, or reused software components are occurring throughout the project life cycle. |  |  |
|  |  | - Assess the impact of non-conformances on the project software's safety, quality, and reliability. |  |  |
| The project manager shall implement process assessments for all high severity software non-conformances (closed loop process). | SWE-204 | - Perform or confirm that a root cause analysis has been completed on all identified high severity software nonconformances, and that the results are recorded and have been assessed for adequacy. |  |  |
|  |  | - Confirm that the project analyzed the processes identified in the root cause analysis associated with the high severity software non-conformances. |  |  |
|  |  | - Assess opportunities for improvement on the processes identified in the root cause analysis associated with the high severity software non-conformances. |  |  |
|  |  | - Perform or confirm tracking of corrective actions to closure on high severity software non-conformances. |  |  |
| ## Software Project Management Peer Reviews |  |  |  |  |
| The project manager shall perform and report the results of software peer reviews or software inspections for: - Software requirements. Software plans, including cybersecurity. Any design items that the project identified for software peer review or software inspections according to the software development plans. Software code as defined in the software and or project plans. Software test procedures. | SWE-087 | - Confirm that software peer reviews are performed and reported on for project activities. |  |  |
|  |  | - Confirm that the project addresses the accepted software peer review findings. |  |  |
|  |  | - Perform peer reviews on software assurance and software safety plans. |  |  |
| The project manager shall, for each planned software peer review or software inspection: - Use a checklist or formal reading technique (e.g., perspective-based reading) to evaluate the work products. Use established readiness and completion criteria. Track actions identified in the reviews until they are resolved. Identify the required participants. | SWE-088 | - Confirm that the project meets the NPR 7150.2 criteria in "a" through "d" for each software peer review. |  |  |
|  |  | - Confirm that the project resolves the actions identified from the software peer reviews. |  |  |
|  |  | - Perform audits on the peer-review process. |  |  |
| The project manager shall, for each planned software peer review or software inspection, record necessary measurements. | SWE-089 | - Confirm that the project records the software peer reviews and results of software inspection measurements. |  |  |

| # NPR 7150.2D Audit Summary |  |  |
| --- | --- | --- |
| Compliance Levels | Number | Notes |
| Compliances |  |  |
| Non-Compliances |  |  |
| Not Applicable |  |  |
| Comments: |  |  |

# NPR 7150.2D Audit Conclusions

Product is [sufficient/not sufficient] to meet product objective(s).

Conclusion Summary:

# Form Usage Guidance and Notes

The results of this audit serve as input to the completion of the NPR 7150.2D / NASA-STD-8739.8B Requirements/Compliance Mapping Matrix. The applicability of each SWE requirement and/or SA task is dependent on any tailoring done on the NPR 7150.2D and NASA-STD-8739.8B Requirements Mapping Matrices. Provide objective evidence to justify each compliance evaluation. Compliance Abbreviations: F = Full compliance, P = Partial compliance, N = Non-compliance, NA = Not applicable If a step is P or N, document the Risk to project delivery in the “Evidence and Comments” cell. Summarize the audit findings in Audit Summary “Notes” cells. The project may also be the supplier, or the supplier may be integrated into the project’s plans, processes, and tasks. The project would ensure that each supplier performs these implementation, verification, validation, test, release, and delivery steps.