The Software System Design Review (SDR) exit criteria outlined in NASA-HDBK-2203, Topic 7.09, ensure that the software's high-level architectural design is well-defined, feasible, and aligned with system-level goals and requirements. The SDR verifies that the software design provides a solid architecture for implementation and that all risks, trade-offs, and requirements are carefully considered.

Documents or sections in a document are identified by Bold Blue text.

| # | Criteria | Y/N | Comments |
| --- | --- | --- | --- |
| A | Architecture Definition |  |  |
| A1 | High-Level software architecture: A high-level software architecture must be identified and documented, showing how the software will meet the functional, performance, and interface requirements. |  |  |
| A2 | Software Architecture: The architecture must define significant components, subsystems, modules, data flows, and interconnections. |  |  |
| B | Requirements Traceability |  |  |
| B1 | Software Architecture: The software architecture and design must be traceable to all system-level and software requirements. |  |  |
| B2 | Software Requirements: All high-level software components must map to specific requirements, including functional, performance, safety, security, and interface requirements. |  |  |
|  | - Software requirements include requirements for COTS, GOTS, MOTS, OSS, reused software components, interface requirements, fault management software requirements, and software-related safety constraints, controls, and mitigations. |  | From earlier version of MCR. |
|  | - The software requirements are testable. |  | From earlier version of MCR. |
|  | - The software requirements address the Software Fault Tree Analysis (FTA) or Software Failure Modes and Effects Analysis results. |  | From earlier version of MCR. |
|  | - TBD and TBR items are identified with acceptable plans and schedules for their disposition, and the software volatility metric is less than 30%. The % of TBD/TBC/TBRs in the software requirements document does not exceed 20% |  | From earlier version of MCR. |
|  | - High software requirements quality risk score (software requirements quality score of 3 or higher). Less than 3 is a risk, and fewer than 20% of the requirements have a high-risk or very high-risk score.. |  | From earlier version of MCR. |
|  | - A sufficient number of detailed software requirements exist. |  | From earlier version of MCR. |
|  | - Software cybersecurity requirements are defined. |  | From earlier version of MCR. |
|  | - Operational scenarios are defined enough to support the definition and allocation of software requirements |  | From earlier version of MCR. |
|  | - Bi-directional traceability is complete with the system, hardware, and ICD requirements. |  | From earlier version of MCR. |
|  | - Transparent allocation of system requirements to software and software architectural elements |  | From earlier version of MCR. |
| C | Interface Definition |  |  |
| C1 | Software Interfaces: All software interfaces (internal and external) must be documented, including data formats, messaging, and communication protocols. |  |  |
| C2 | Software Interfaces: must address hardware/software integration points and external interactions. |  |  |
| D | Feasibility and Trade Studies |  |  |
| D1 | Software Concept: Feasibility of the proposed design must be demonstrated, considering all resource constraints (e.g., cost, performance, and schedule). |  |  |
| D2 | Software Concept: Completed trade studies or analyses must justify design decisions and demonstrate that the selected approach balances mission priorities. |  |  |
| E | Risk Assessment and Mitigation Plans |  |  |
| E1 | Software Risks: Risks associated with the architecture, including technical, schedule, or cost risks, must be identified and assessed. |  |  |
|  | - NASA has access to the software products in electronic format, including software development and management metrics. |  | From earlier version of MCR. |
|  | - The planned use of software static code analysis is acceptable. |  | From earlier version of MCR. |
|  | - Software risks, issues, and findings are documented.. |  | From earlier version of MCR. |
|  | - The project has addressed all software assurance and Severity 1 or 2 findings. |  | From earlier version of MCR. |
|  | - Verify that the project does not have a risk associated with developing software at the same time as the hardware is being designed, the risk of misunderstanding the software-hardware interfaces, and not having the hardware available to use in the software development. |  | From earlier version of MCR. |
|  | - Software supply chain risks. |  | From earlier version of MCR. |
|  | - Sufficient software workforce or software skillsets exist |  | From earlier version of MCR. |
| E2 | Software Risks: Mitigation plans must be documented for all identified risks. |  |  |
| F | Preliminary Data Management |  |  |
| F1 | Data Management Requirements: Data management requirements (e.g., data storage, access, and flows) must be addressed in the high-level design. |  |  |
| F2 | Key data structures, databases, and storage solutions: must be preliminarily defined and reviewed. |  |  |
| G | Safety and Security Considerations |  |  |
| G1 | Software Design – Safety-Critical: Safety-critical aspects of the design must be identified, and appropriate controls defined in the architecture. |  |  |
| G2 | Security Design: Security considerations, including protection against cyber threats, must be integrated into the high-level design. |  |  |
| G3 | Preliminary Software Hazard Analysis Identification of software safety-critical components by having a preliminary software hazard analysis completed |  | From earlier version of MCR. |
|  | - The software hazards are clearly defined. |  | From earlier version of MCR. |
|  | - Traceability between software requirements and hazards is complete. |  | From earlier version of MCR. |
|  | - Hazard controls are defined. |  | From earlier version of MCR. |
|  | - Hazard verifications are defined. |  | From earlier version of MCR. |
|  | - All software requirements that trace to a hazard analysis are to be verified by test. |  | From earlier version of MCR. |
|  | - Software hazards address the software Failure Modes and Effects Analysis (FEMAs) and software Fault Tree results. |  | From earlier version of MCR. |
| H | Verification and Validation (V&V) Planning |  |  |
| H1 | Software Design: A preliminary plan for verifying the high-level design must be defined. |  |  |
| H2 | Software Architecture: The architecture must demonstrate that it supports the verification and validation of all software requirements. |  |  |
| I | Compliance with Standards |  |  |
| I1 | Software Design: The design must comply with relevant software, system, and safety standards (e.g., NASA-STD-8719.13 and NASA-STD-8739.8). |  |  |
| I2 | Software Design: Reviews must confirm adherence to agency guidelines and project-specific standards. |  |  |
| J | Stakeholder Approval |  |  |
| J1 | Software Key Stakeholders: Key stakeholders, including systems engineers, project managers, and software assurance teams, must review and approve the architecture. |  |  |
| J2 | Feasibility And Readiness: Agreement on the feasibility and readiness of the architecture must be reached among all parties. |  |  |
| K | Supporting Documentation |  |  |
| K1 | Software Architecture Documents: All documentation related to the software architecture must be complete, reviewed, and approved. This includes design diagrams, interface definition documents, trade studies, and risk analyses. |  |  |
| K2 | Software Architecture Documents : The documentation should provide sufficient detail to transition to detailed design and implementation. |  |  |
| K3 | Software Development Plan: Completed |  | From earlier version of MCR. |
|  | - Adequate planning exists for developing, inserting, or deploying any enabling new software technology or avionics technology needed for software development. |  | From earlier version of MCR. |
|  | - The software schedule satisfies the following conditions: Coordinates with the overall project schedule, Documents the interactions of milestones and deliverables between software, hardware, operations, and the rest of the system, reflects the critical dependencies for software development activities and identifies and accounts for dependencies with other projects and cross-program dependencies. |  | From earlier version of MCR. |
|  | - The proposed avionics/software architecture is credible and responsive to program requirements and constraints, including supporting the single-point failure/Fault Tolerance requirements. |  | From earlier version of MCR. |
|  | - The planned use of software static code analysis is acceptable. |  | From earlier version of MCR. |
| K4 | Completed Software Classification and Safety Criticality Assessments: are available |  | From earlier version of MCR. |
| K5 | NASA NPR 7150.2 requirements mapping matrix: is complete |  | From earlier version of MCR. |
|  | - The correct software classifications have been defined. |  | From earlier version of MCR. |
| K6 | NASA-STD-8739.8 requirements mapping matrix: is complete |  | From earlier version of MCR. |
| K7 | Software Data Dictionary |  | From earlier version of MCR. |
| K8 | Completed Software Safety Assessment |  | From earlier version of MCR. |
| K9 | Completed software assurance software requirements analysis |  | From earlier version of MCR. |
| K10 | Completed the IV&V software requirements analysis |  | From earlier version of MCR. |
| K11 | Completed peer review(s) of the software requirements |  | From earlier version of MCR. |
| K12 | Completed peer review(s) of the software plans |  | From earlier version of MCR. |
| K13 | Preliminary Human Rating Plan, if applicable |  | From earlier version of MCR. |
| K14 | Preliminary Maintenance Plan |  | From earlier version of MCR. |
| K15 | Software configuration management (CM) plan |  | From earlier version of MCR. |
| K 16 | Completed IV&V Project Execution Plan |  | From earlier version of MCR. |
| K17 | Identify the software assurance, software safety, and IV&V personnel for the project and milestone review. |  | From earlier version of MCR. |
| K18 | The software assurance point of contact for the project has been identified. |  | From earlier version of MCR. |
| K19 | Software Metrics: to track the software quality and maturity have been selected. |  | From earlier version of MCR. |
|  | - The software technical metric margins are defined and are acceptable. |  | From earlier version of MCR. |
|  | - Adequate technical and programmatic margins (e.g., data throughput, memory, CPU utilization) and resources exist to complete the software development within budget, schedule, and known risks |  | From earlier version of MCR. |
| K20 | Certifiable Software Development Practices: by the organizations developing the critical software components exist and are being followed. |  | From earlier version of MCR. |
|  | - Evidence exists with Software process audit results. |  | From earlier version of MCR. |
|  | - Evidence that the software development organization followed the required processes for this point in the software lifecycle. |  | From earlier version of MCR. |
|  |  |  | From earlier version of MCR. |
| L | Readiness for Detailed Design |  |  |
| L1 | Software Design: The project must demonstrate readiness to proceed to the detailed software design phase. |  |  |
| L2 | Confirm that RFAs and RIDs from MCR: have been satisfactorily resolved |  | From earlier version of MCR. |
| L3 | Critical Design Issues: All critical design issues raised at the SDR must be resolved or have approved paths toward resolution. |  |  |
|  | - IV&V concurs that the project’s software plans, schedules, resources, and requirements are sufficiently mature to begin Phase B (If IV&V is required) |  | From earlier version of MCR. |

Summary of Review