The PDR demonstrates that the preliminary design meets all system requirements with acceptable risk and within the cost and schedule constraints and establishes the basis for proceeding with detailed design. It shows that the correct design option has been selected, interfaces have been identified, and verification methods have been described. Full baseline costs and schedules, as well as risk assessments, management systems, and metrics, are presented.

# Prelimary Design Review (SDR)– Checklist Software Criteria; Y/N; Notes. Have the software requirements been fully baselined, verified as complete and testable, and are TBD/TBR items within required thresholds (≤1%) with volatility <20%?. Does the preliminary software design demonstrably meet all baselined software requirements—including safety-critical, FTA/FMEA-derived, cybersecurity, and interface requirements—with adequate technical margins (CPU, memory, throughput)?. Has bi-directional traceability been established and validated between system requirements, software requirements, design modules, interfaces, hazards, and fault-management requirements?. Are all software hazards clearly defined, mapped to requirements, assigned controls, and associated with verifiable test methods—and are preliminary FTA/FMEA results incorporated into the design?. Does the software design sufficiently define architecture, components, interfaces, operational modes/states, error detection, command/telemetry handling, and safety-critical isolation needed to begin detailed design and coding?. Have IV&V and Software Assurance completed their requirements and design analyses and concurred that maturity is adequate to proceed to CDR?. Are software development tools, facilities, engineering test units, and models/simulations identified, validated/accredited where needed, and available when required to support implementation and verification?. Are software development processes, change control, problem reporting, configuration management, and process audit results in place and providing evidence of disciplined, certifiable engineering practices?. Are high-level and preliminary software test plans defined—including integration/test levels, prototype evaluations (if applicable), and verification strategies aligned with all requirement types (functional, safety, performance, cyber, hazard-linked)?. Are project-level artifacts—trade studies, baselined software schedule, cost estimate, operational concepts, and acceptance criteria—complete, credible, and consistent with the software’s preliminary design and certification path?. # Section 2 — Detailed Software Criteria

| Criteria | Y/N | Comments |
| --- | --- | --- |
| Design and Requirements Verification |  |  |
| Baselined Software Requirements Specification: Baseline established at the software level. |  |  |
| - Adequate documentation exists to allow proceeding with software implementation and software testing. |  |  |
| - All software requirements are verifiable. |  |  |
| - All Safety mission-critical software designs/requirements have been through a peer review. Peer reviews have required participation |  |  |
| - TBD and TBR items are identified with acceptable plans and schedules for their disposition, and the software volatility metric is less than 20%. The % of TBD/TBC/TBRs in the software requirements document does not exceed 1% |  |  |
| - High software requirements quality risk score (software requirements quality score of 3 or higher). Less than 3 is a risk, and fewer than 20% of the requirements have a high-risk or very high-risk score |  |  |
| - Software requirements volatility is less than 20%. |  |  |
| - A sufficient number of detailed software requirements exist. |  |  |
| - The software requirement volatility metric is less than 30%. |  |  |
| - The detailed software requirements are agreed upon, finalized, stated clearly, and consistent with the preliminary design. |  |  |
| - The software requirements reflect and include the Software Fault Tree Analysis (FTA), or Software Failure Modes and Effects Analysis results |  |  |
| - Requirements on Off the Shelf Software are baselined and documented. |  |  |
| Preliminary Software Design Description: Preliminary detailed design meets software requirements with adequate margins |  |  |
| - The software's preliminary design features and architecture are represented by software requirements. |  |  |
| - Adequate technical and programmatic margins (e.g., data throughput, memory) and resources exist to complete the software development within budget, schedule, and known risks. |  |  |
| - Relevant software operational modes and states are defined (e.g., nominal, critical, contingency). |  |  |
| - Software common cause addressed (if applicable). |  |  |
| - Software design addresses the software safety-critical requirements. |  |  |
| - Software design addresses unauthorized use of software applications, command issuing, memory changes, and data changes to the software configuration. |  |  |
| - Software design provides automatic detection and safing for critical and catastrophic hazards. |  |  |
| - Software fault management requirements, architecture, and design have been defined. |  |  |
| - The software design logically isolates the safety-critical design elements and data from non-safety-critical data. |  |  |
| - The Software command and telemetry design have been defined. |  |  |
| - Software error detections have been defined. |  |  |
| - Software design, architecture, components, and interfaces are defined and understood at the level needed for code development. |  |  |
| - Software design addresses the Software Fault Tree Analysis (FTA) or Software Failure Modes and Effects Analysis results. |  |  |
| - Cybersecurity has been addressed in the software design. |  |  |
| Bidirectional Traceability: Exists between software requirements and design modules. |  |  |
| Baselined Software Architecture: Exists and interfaces are defined. |  |  |
| Preliminary Software Data Dictionary: Exists and data is defined |  |  |
| Software Requirements Analysis: Completed the IV&V Software Requirements Analysis |  |  |
| Software Design Analysis: Completed IV&V Software Design Analysis |  |  |
| Software Requirements Analysis: Completed Software Assurance Software Requirements Analysis |  |  |
| Software Design Analysis: Completed Software Assurance Software Design Analysis |  |  |
| Concurance: IV&V concurs that the project’s software requirements and design are sufficiently mature to proceed to CDR. (If IV&V is required) |  |  |
| Risk and Hazard Analysis |  |  |
| Software Hazards: Identified and addressed in System Hazard Analyses: include all known software hazards |  |  |
| - The software hazards are clearly defined. |  |  |
| - Traceability between software requirements and hazards is complete. |  |  |
| - Hazard controls are defined.. |  |  |
| - Hazard verifications are defined. |  |  |
| - All software requirements that trace to a hazard analysis are to be verified by test. |  |  |
| - Software hazards address the software Failure Modes and Effects Analysis (FEMAs) and software Fault Tree results. |  |  |
| Software Fault Tree Analysis (FTA): Preliminary results available. |  |  |
| Safety and Mission Risks: Understood and credibly assessed |  |  |
| Compliance and Standards |  |  |
| Updated NPR 7150.2 and NASA-STD-8739.8 Requirements Mapping: Tailoring completed and approved. |  |  |
| Software Classifications and Safety-Criticality: Updated as necessary. |  |  |
| Tools and Facilities |  |  |
| Software Development Tools: Identified, including computers programming language, and facilities for implementation. |  |  |
| - sufficient software analysis and development tools exist. |  |  |
| - the software development organization is trained in the use of the software language. |  |  |
| - Validated and accredited software tool(s) required to develop or maintain software exist. A defined approach to the automatic generation of software source code exists. |  |  |
| Software Development Facilities: Planned and will be in place when needed. |  |  |
| Resource Utilization: Estimates and margins provided. |  |  |
| Hardware resources: develop and test the software. The required Engineering test units, modeling, and simulations have been identified and planned |  |  |
| Quality Assurance and Process Audit |  |  |
| Software Process Audit Results: Available. |  |  |
| Software Development Processes and Practices: by the organizations developing the critical software components exist and are being followed. |  |  |
| - Evidence exists with Software process audit results. |  |  |
| - Evidence that the software development organization followed the required processes for this point in the software lifecycle. |  |  |
| Problem Reporting Process: Acceptable and includes tracking and resolution. |  |  |
| - Change control is established (e.g., change tracking, review, approval, disapproval, change impact analysis, resolution, re-validation, and re-verification.) |  |  |
| Documentation and Metrics |  |  |
| Interface Control Documents: Sufficiently mature for Critical Design Review (CDR). Avionics architecture, components, and interfaces are defined and understood at the level needed to move to CDR |  |  |
| - The project has identified software quality attributes in the software architecture definition. |  |  |
| Software Metrics: In use to track software quality and maturity. |  |  |
| - Software risks, issues, and findings are documented. |  |  |
| - The project has addressed all software assurance and Severity 1 or 2 findings. |  |  |
| - Verify that the project does not have a risk associated with developing software at the same time as the hardware is being designed, the risk of misunderstanding the software-hardware interfaces, and not having the hardware available to use in the software development. |  |  |
| - Software supply chain risks. |  |  |
| - Sufficient software workforce or software skillsets exist. |  |  |
| Baselined Software Configuration Management Plan: Processes and tools are in place. |  |  |
| Software Products in electronic format: NASA has access to the software products in electronic format, including software development and management metrics. |  |  |
| Stakeholder and Organizational Readiness |  |  |
| IV&V Concurrence: Software requirements and design are mature for CDR. |  |  |
| Certifiable Practices: Followed by organizations developing critical software components. |  |  |
| Software Assurance Personnel: Identified for the project and milestone review. |  |  |
| Testing and Validation Plans |  |  |
| High-Level Test Plan: Identifies testing needed at each level of implementation/integration. |  |  |
| Preliminary Software Test Plans: Developed and documented. |  |  |
| Prototype Software: If applicable, developed and evaluated. |  |  |
| Reviews and Approvals |  |  |
| Peer Reviews: Completed for software preliminary design and requirements. |  |  |
| Configuration Control Board: Established and Change Control Process in place. |  |  |
| Lessons Learned: Documented from software areas of the project. |  |  |
| Project Management and Cost Estimates |  |  |
| Software Trade Studies: Completed. |  |  |
| Baselined Cost Estimate: Provided for project’s software support. |  |  |
| Baselined Operational Concepts: Defined and documented. |  |  |
| Baselined Software Schedule: Documented and available. |  |  |
| Preliminary Acceptance Criteria: Documented and available. |  |  |
| Open paper work |  |  |
| RFAs and RIDs from the previous review: have been resolved, and any resulting actions are complete. |  |  |
| Use of SI |  |  |
| SI Scope & ODD Accepted: Review board concurs that the SI functions, autonomy bounds, and ODD definition are sufficiently complete for preliminary design, with identified gaps and closure plans. 12 |  |  |
| Risk‑Based Credibility Path Committed: The project has an agreed risk/criticality level for SI models/sims and a plan to reach target credibility levels (incl. uncertainty quantification) before TRR/CDR as applicable. |  |  |
| Data Readiness & Governance Accepted: Dataset quality/coverage meet PDR expectations; data lineage, controls, and FAIR/FAIRUST practices are baselined with actions for any deficiencies. |  |  |
| Bias/Ethics Mitigations Baseline: Identified bias risks have measurable mitigations and thresholds; governance agrees on acceptance criteria and monitoring plans. |  |  |
| Model Requirements Traceability Baseline: SI requirements (performance/robustness/latency/interpretability/safety) trace to hazards, scenarios, and data; bi‑directional traceability is established per SWEHB/NPR. |  |  |
| V&V Strategy Approved (incl. Uncertainty Reporting): The board accepts the SI V&V plan consistent with 7009B—including validation referents, sensitivity analysis, and reporting of uncertainty/credibility to decision-makers. |  |  |
| Assurance Case Baseline Approved: Initial SI assurance case or plan (claims/arguments/evidence plan) is approved with maturation checkpoints to CDR/FRR; objective evidence mapping aligns with NASA-HDBK-2203. |  |  |
| Runtime Monitoring & Fallbacks in Preliminary Design: Preliminary algorithms/architectures for drift/anomaly detection, confidence checks, and verified fail-safe transitions are in the design and scheduled for implementation testing. |  |  |
| Human-in-the-Loop Controls & HMI Accepted: Operator visibility/override, alerts, and workload impacts are in scope with usability evaluation plans. |  |  |
| Cybersecurity Controls for SI Stack Accepted: Controls for SI-specific threats (poisoning/adversarial/model exfiltration) are baselined, consistent with Agency SI governance expectations. |  |  |
| Configuration Management of Models & Data Baseline: CM items for datasets, models, training pipelines, and metadata are under version control with auditability; nonconformance handling is defined. |  |  |
| Simulation/Testbed Fidelity and Scenario Library Accepted: The sim/test environment fidelity is adequate for PDR; scenario coverage (nominal/off-nominal) and credibility assessment approach are approved. |  |  |
| Tailoring Decisions Ratified: Engineering and SMA Technical Authorities concur with SI-specific tailoring against 7.09/NPR 7123 Appendix G; open tailoring RFAs have closure plans. |  |  |
| Objective Evidence Closeout Plan: A schedule exists to deliver SI evidence (data/model cards, bias/robustness reports, uncertainty summaries, assurance case updates) ahead of CDR/TRR milestones |  |  |
| Risk, Schedule, and Budget Credibility for SI Work: Estimates reflect SI data curation, tooling, compute, lab/sim time, V&V, and assurance; risks/mitigations are credible to proceed to detailed design. |  |  |

Summary of Review