The Software Test Readiness Review (TRR) exit criteria, as outlined in NASA-HDBK-2203, Topic 7.09, lay out the necessary conditions that must be met before software testing can begin. The TRR ensures that all preparations for testing—such as software, hardware, test environments, and documentation—are complete and that the team is ready to proceed with testing activities. The focus is on validating that the planned tests will address requirements, identify defects, and measure performance and functionality effectively.

Documents or sections in a document are identified by Bold Blue text.

| # | Criteria | Y/N | Comments |
| --- | --- | --- | --- |
| A | Test Objectives and Scope |  |  |
| A1 | Test Objectives: Clearly defined test objectives must be aligned with the requirements and mission objectives, ensuring that testing will validate software functionality, performance, reliability, and safety. |  |  |
| B | Test Plans and Procedures |  |  |
| B1 | Software Test Plans, Procedures, and Scripts: Test plans, procedures, and scripts must be complete, reviewed, and approved. |  |  |
|  | - These documents should detail the schedules, test cases, specific steps, expected results, and acceptance criteria. |  |  |
|  | - Confirm processes and procedures are in place for testing. Including procedures in place for capturing test results, and reporting discrepancies. |  | From earlier version of TRR. |
|  | - Confirm TRR-specific materials are available (e.g., test plans, test procedures, test cases, version descriptions document, test schedule, test status, test data) |  | From earlier version of TRR. |
|  | - Acceptable planned use of STB (Simulation Test Bed) instead of using flight hardware for flight certification. |  | From earlier version of TRR. |
|  | - The OTS software components will be verified and validated to the same level required to accept a similarly developed software component for its intended use. |  | From earlier version of TRR. |
|  | - Software verification approach and regression testing approach are established for the project. |  | From earlier version of TRR. |
|  | - The software testing approach is comprehensive, and the planning for system assembly, integration, test, and launch site and mission operations is sufficient to progress into the next phase. |  | From earlier version of TRR. |
|  | - Software verification approach and regression testing approach are established for the project. |  | From earlier version of TRR. |
|  | - Engineering test units, modeling, and simulations have been developed and certified per plan. |  | From earlier version of TRR. |
|  | - Verify that the project does not have a risk associated with developing software at the same time as the hardware is being designed, the risk of misunderstanding the software-hardware interfaces, and not having the hardware available to use in the software development. |  | From earlier version of TRR. |
|  | - The software verification and validation requirements and plans are complete, including stress testing, end-to-end testing, fault management, unauthorized use of software applications, command issuing, memory changes, data changes to the software configuration, and software regression testing plans. |  | From earlier version of TRR. |
|  | - Software test procedures are complete, bi-directional traceability between the software requirements and software test procedures is complete, and the software test coverage approach is approved. |  | From earlier version of TRR. |
|  | - All Safety mission-critical software test procedures have been through a peer review. Peer reviews have required participation. |  | From earlier version of TRR. |
|  | - The software configuration data has been tested. |  | From earlier version of TRR. |
|  | - Informal software test runs are completed |  | From earlier version of TRR. |
|  | - An acceptable approach for independent software testing is planned. |  | From earlier version of TRR. |
| B2 | Software Procedures: Procedures must ensure adequate coverage of all functional and non-functional requirements. |  |  |
|  | - Confirm any necessary verification of computations has been completed. |  | From earlier version of TRR. |
|  | - Expected results defined. |  | From earlier version of TRR. |
|  | - Verification of end-to-end functional flows and database linkages. |  | From earlier version of TRR. |
|  | - Verification of performance throughout the anticipated range of operating conditions, including nominal, abnormal, failure, and degraded mode situations. |  | From earlier version of TRR. |
| C | Requirements Traceability |  |  |
| C1 | Software Requirements: All software requirements, including functional, performance, and safety requirements, must be traceable to corresponding test cases. |  |  |
|  | - Confirm that end-to-end functional flows and database linkages will be tested |  | From earlier version of TRR. |
|  | - Verification of computations using nominal and stress data. |  | From earlier version of TRR. |
| C2 | Software Requirements: Gaps in test coverage, if any, should be identified and addressed. |  |  |
| C3 | Software Requirements: The software requirements are baselined, and adequate documentation exists to allow proceeding with software implementation and software testing. |  |  |
|  | - All software requirements are verifiable. |  | From earlier version of TRR. |
|  | - All Safety mission-critical software designs/requirements have been through a peer review. Peer reviews have required participation. |  | From earlier version of TRR. |
|  | - TBD and TBR items are identified with acceptable plans and schedules for their disposition, and the software volatility metric is less than 20%. The % of TBD/TBC/TBRs in the software requirements document does not exceed 1%. |  | From earlier version of TRR. |
|  | - The total software requirements quality risk score is above 4 with 0% of the detailed software requirements scoring at a high or very high-risk level. |  | From earlier version of TRR. |
|  | - The software requirement volatility is less than 5%. |  | From earlier version of TRR. |
| D | Readiness of Test Artifacts |  |  |
| D1 | Software Test Inputs, Test Cases, Test Data, Sample Scenarios: All test inputs, such as test cases, test data, sample scenarios, and associated documentation, must be prepared and validated. |  |  |
|  | - Databases for integration and testing have been created and validated. |  | From earlier version of TRR. |
| D2 | Software Expected Outputs and Success Criteria: Expected outputs and success criteria for tests must be clearly defined and documented. |  |  |
| E | Test Environment Validation |  |  |
| E1 | Software Test Environment: The test environment, including hardware, simulators, testbeds, facilities, and tools, must be set up and verified for accuracy and consistency. |  |  |
|  | - Test network showing interdependencies among test events and planned time deviations for these activities prepared. |  | From earlier version of TRR. |
|  | - Test Plans, Test Procedures, Test Cases with applicable data, Test Scenarios, Test Environment. |  | From earlier version of TRR. |
| E2 | Software Environment Configurations: Environment configurations should mimic operational conditions as closely as possible. |  |  |
| F | Software Baseline Readiness |  |  |
| F1 | Software to be Tested: The software to be tested must be complete, stable, and built to the appropriate configuration baseline (commonly the integration or pre-release version). |  |  |
| F2 | Software to be Tested: The software should be free of critical defects that would block testing. |  |  |
|  | - Confirm that all known discrepancies are identified and addressed in an agreed-upon manner. |  | From earlier version of TRR. |
| G | Interface Readiness |  |  |
| G1 | Software Interfaces: All software interfaces, both internal and external, must be defined, implemented, tested, and validated to enable testing activities. |  |  |
| G2 | Software Interfaces: Any dependencies on external systems or hardware should be met and functional. |  |  |
| H | Issue and Risk Management |  |  |
| H1 | Software Issues: All known software issues, risks, and non-conformances must be documented and assessed for their impact on testing. |  |  |
|  | - Verify that the project does not have a risk associated with developing software at the same time as the hardware is being designed, the risk of misunderstanding the software-hardware interfaces, and not having the hardware available to use in the software development. |  | From earlier version of TRR. |
| H2 | Software Risks: Risks that could impact the testing process should have mitigation plans in place. |  |  |
| H3 | Safety-critical and Security: Safety-critical and security considerations have been identified. |  | From earlier version of TRR. |
|  | - The project has addressed all software assurance and Severity 1 or 2 findings. |  | From earlier version of TRR. |
|  | - All identified safety-critical software components have a cyclomatic complexity value of 15 or lower. |  | From earlier version of TRR. |
|  | - 100 percent code test coverage has been achieved for all identified safety-critical software components using the Modified Condition/Decision Coverage (MC/DC) criterion. |  | From earlier version of TRR. |
| H4 | Hazard Analysis: System Hazard Analyses address or include all known software hazards, |  | From earlier version of TRR. |
|  | - The software hazards are clearly defined. |  | From earlier version of TRR. |
|  | - Traceability between software requirements and hazards is complete. |  | From earlier version of TRR. |
|  | - Hazard controls are defined. |  | From earlier version of TRR. |
|  | - Hazard verifications are defined. |  | From earlier version of TRR. |
|  | - All software requirements that trace to a hazard analysis are to be verified by test. |  | From earlier version of TRR. |
|  | - Software hazards address the software Failure Modes and Effects Analysis (FEMAs) and software Fault Tree results. |  | From earlier version of TRR. |
| I | Test Team Preparedness |  |  |
| I1 | Software Testers: Personnel involved in the testing should have adequate training and a clear understanding of their roles and responsibilities. |  |  |
| I2 | Software Testers: The team should be prepared to follow the test procedures and handle anomalies during testing. |  |  |
|  | - Have an agreed-upon plan for SA review of testing (witnessing, sampling, etc.) |  | From earlier version of TRR. |
| J | Configuration and Quality Assurance Readiness |  |  |
| J1 | Software Configuration Management: Configuration management must be in place to ensure traceability and control over changes to software, test plans, and test artifacts. |  |  |
|  | - The software build was created from CM and is ready for testing. |  | From earlier version of TRR. |
|  | - Successful functional configuration audit (FCA) of the version description document (VDD) (such as FSW), including fixes. |  | From earlier version of TRR. |
| J2 | Software Concept: Quality assurance plans or processes must confirm that testing will be conducted in compliance with relevant standards. |  |  |
| K | Approval to Execute Tests |  |  |
| K1 | Software Stakeholders: Stakeholders (e.g., project managers, software assurance teams, and engineers) must review and formally approve the readiness to enter testing based on the status of test plans, procedures, and test environment setup. |  |  |
| L | Problem Reporting and Tracking |  |  |
| L1 | Software Issue Tracking During Testing: A system for identifying, tracking, and resolving test anomalies, failures, or defects must be established and ready to be used during testing. |  |  |
|  | - Confirm any problems/issues have been documented. |  | From earlier version of TRR. |
| M | Documentation Completeness |  |  |
| M1 | Software Pre-Test Planning Documents: All pre-test planning documents, including test plans, configuration information, safety assessments, and operational checklists, must be provided, reviewed, and approved. |  |  |
| N | General Readiness |  | From earlier version of TRR. |
| N1 | Previous Design Review Success Criteria: All previous design review success criteria and critical issues were satisfied per the agreed-upon plan. |  | From earlier version of TRR. |
| N2 | Code Reviews: Completed code reviews and walkthroughs, test plans and test procedures, peer reviews |  | From earlier version of TRR. |
| N3 | Secure Coding Standards: Confirm adherence to a secure coding standard. |  | From earlier version of TRR. |
| N4 | Audits or Assessments of Documentation and Processes: Confirm audits or assessments of documentation and processes have been performed throughout the implementation. |  | From earlier version of TRR. |
|  | - Certifiable software development practices by the organizations developing the critical software components exist and are being followed. |  | From earlier version of TRR. |
|  | - Evidence exists with Software process audit results. |  | From earlier version of TRR. |
|  | - Evidence that the software development organization followed the required processes for this point in the software lifecycle. |  | From earlier version of TRR. |
| N5 | Version Description Document: Confirm readiness of the VDD. |  | From earlier version of TRR. |
|  | - Completed functional configuration audit of the VDD. |  | From earlier version of TRR. |
|  | - The software Version Description Document is complete and accurate. |  | From earlier version of TRR. |
| N6 | Software Test Analysis: Completed Software Test Analysis is available and issues found during analysis are resolved. |  | From earlier version of TRR. |
| N7 | Waivers and Deviations: Confirm any waivers or deviations are approved. |  | From earlier version of TRR. |
| N8 | Prior Testing of Code: Applicable functional, unit-level, subsystem, system, and qualification testing were conducted successfully and reviewed. |  | From earlier version of TRR. |
|  | - Informal dry run completed without errors. |  | From earlier version of TRR. |
|  | - The software test data has been reviewed and analyzed for expected results, and the results are consistent with the test plans and objectives. |  | From earlier version of TRR. |
| N9 | Baselined Documentation: Confirm that all baselined documents from previous reviews are available. |  | From earlier version of TRR. |
| N10 | Lessons learned: captured from the software areas of the project. |  | From earlier version of TRR. |
| N11 | Software Change Requests: Outstanding software change requests (SCRs) ready for review |  | From earlier version of TRR. |
| N12 | Operations and User Manuals: Validation of operations and user manuals completed. |  | From earlier version of TRR. |
| N13 | Software Static Code Analysis : All software static code analysis has been completed, and the appropriate findings have been corrected. |  | From earlier version of TRR. |
| N14 | Software data dictionary: fields are correct and complete and have been tested.The software configuration data has been tested. |  | From earlier version of TRR. |
| N15 | Software structural quality: is evident in the software products. |  | From earlier version of TRR. |
|  | - Software architecture quality exists. |  | From earlier version of TRR. |
|  | - The code is maintainable. |  | From earlier version of TRR. |
|  | - Safety-critical and secure coding standards are used. |  | From earlier version of TRR. |
|  | - Code is fault tolerance. |  | From earlier version of TRR. |
|  | - The code is secure. |  | From earlier version of TRR. |
|  | - The code is testable. |  | From earlier version of TRR. |
| N16 | IV&V concurance: IV&V concurs that the project’s software requirements, design, and testing are sufficiently mature to proceed to software testing and integration. (If IV&V is required) |  | From earlier version of TRR. |

Summary of Review